## GANTT
|  | Phase 1: Preparation | [5 empty] | Phase 2: Case study | [5 empty] | Phase 3: Experiment | [8 empty] | Phase 4: Finalizing
|  | FEB |  |  | MAR |  |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  |  | JUL
|  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
1 | Thesis proposal | bar: FEB 7
2 | Finalize methodology
3 | Preparing survey and interviews
4 | Literature review | bar: MAR 11
5 | Survey
6 | Expert interviews
7 | Preparing experiment phase
8 | Draft results section: analysis and results | bar: APR 16
9 | Experiments and analysis
10 | Results, discussion and conclusions
11 | Draft thesis | bar: JUN 24
13 | Final delivery | bar: JUL 30

## Deadlines
A | 7 | 2023-02-19 22:00 | Thesis design
B | 11 | 2023-03-19 22:00 | Draft Literature Review
C | 15 | 2023-04-16 22:00 | Draft Metholodogy Section
D | 20 | 2023-05-21 22:00 | Draft Results Section Analysis and Results
E | 24 | 2023-06-18 22:00 | Draft Thesis
F | 26 | 2022-07-31 22:00 | Final delivery

## Week numbers
weeknummers.com/weeknummers/2023/
1 | 2023-01-02 | 2023-01-08
2 | 2023-01-09 | 2023-01-15
3 | 2023-01-16 | 2023-01-22
4 | 2023-01-23 | 2023-01-29
5 | 2023-01-30 | 2023-02-05
6 | 2023-02-06 | 2023-02-12 | Week 6: 06-02-2023 - 12-02-2023
7 | 2023-02-13 | 2023-02-19 | Week 7: 13-02-2023 - 19-02-2023
8 | 2023-02-20 | 2023-02-26 | Week 8: 20-02-2023 - 26-02-2023
9 | 2023-02-27 | 2023-03-05 | Week 9: 27-02-2023 - 05-03-2023
10 | 2023-03-06 | 2023-03-12 | Week 10: 06-03-2023 - 12-03-2023
11 | 2023-03-13 | 2023-03-19 | Week 11: 13-03-2023 - 19-03-2023
12 | 2023-03-20 | 2023-03-26 | Week 12: 20-03-2023 - 26-03-2023
13 | 2023-03-27 | 2023-04-02 | Week 13: 27-03-2023 - 02-04-2023
14 | 2023-04-03 | 2023-04-09 | Week 14: 03-04-2023 - 09-04-2023
15 | 2023-04-10 | 2023-04-16 | Week 15: 10-04-2023 - 16-04-2023
16 | 2023-04-17 | 2023-04-23 | Week 16: 17-04-2023 - 23-04-2023
17 | 2023-04-24 | 2023-04-30 | Week 17: 24-04-2023 - 30-04-2023
18 | 2023-05-01 | 2023-05-07 | Week 18: 01-05-2023 - 07-05-2023
19 | 2023-05-08 | 2023-05-14 | Week 19: 08-05-2023 - 14-05-2023
20 | 2023-05-15 | 2023-05-21 | Week 20: 15-05-2023 - 21-05-2023
21 | 2023-05-22 | 2023-05-28 | Week 21: 22-05-2023 - 28-05-2023
22 | 2023-05-29 | 2023-06-04 | Week 22: 29-05-2023 - 04-06-2023
23 | 2023-06-05 | 2023-06-11 | Week 23: 05-06-2023 - 11-06-2023
24 | 2023-06-12 | 2023-06-18 | Week 24: 12-06-2023 - 18-06-2023
25 | 2023-06-19 | 2023-06-25 | Week 25: 19-06-2023 - 25-06-2023
26 | 2023-06-26 | 2023-07-02 | Week 26: 26-06-2023 - 02-07-2023
27 | 2023-07-03 | 2023-07-09 | Week 27: 03-07-2023 - 09-07-2023
28 | 2023-07-10 | 2023-07-16 | Week 28: 10-07-2023 - 16-07-2023
29 | 2023-07-17 | 2023-07-23 | Week 29: 17-07-2023 - 23-07-2023
30 | 2023-07-24 | 2023-07-30 | Week 30: 24-07-2023 - 30-07-2023
31 | 2023-07-31 | 2023-08-06
32 | 2023-08-07 | 2023-08-13
33 | 2023-08-14 | 2023-08-20
34 | 2023-08-21 | 2023-08-27
35 | 2023-08-28 | 2023-09-03
36 | 2023-09-04 | 2023-09-10
37 | 2023-09-11 | 2023-09-17
38 | 2023-09-18 | 2023-09-24
39 | 2023-09-25 | 2023-10-01
40 | 2023-10-02 | 2023-10-08
41 | 2023-10-09 | 2023-10-15
42 | 2023-10-16 | 2023-10-22
43 | 2023-10-23 | 2023-10-29
44 | 2023-10-30 | 2023-11-05
45 | 2023-11-06 | 2023-11-12
46 | 2023-11-13 | 2023-11-19
47 | 2023-11-20 | 2023-11-26
48 | 2023-11-27 | 2023-12-03
49 | 2023-12-04 | 2023-12-10
50 | 2023-12-11 | 2023-12-17
51 | 2023-12-18 | 2023-12-24
52 | 2023-12-25 | 2023-12-31